## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Gantt Chart
PROJECT: Short Messaging Control Mechanism for CAN Bus Architecture
Kennesaw State University |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Andrew Cline, Clifford Gilbert, Goran Novakovic
Project start date: | 2024-01-31 |  |  |  |  | February | [6 empty] | March | [34 empty] | April
Scrolling increment: | 25 | time axis 2024-02-25 to 2024-04-29
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-02-25 to 2024-04-29
Milestone Reports
#2 - Project Proposal | Milestone | All | 100% | 2024-03-04 | 1 | bar: 2024-03-04
#3 - Progress Report | Milestone | All | 100% | 2024-04-01 | 1 | bar: 2024-04-01
#4 - PowerPoint Presentation | Milestone | All | 0% | 2024-04-15 | 1 | bar: 2024-04-15
#5 - Project Report | Milestone | All | 0% | 2024-04-29 | 1 | bar: 2024-04-29
Project Selection
Define Project Goals | On Track | All | 100% | 2024-02-28 | 1
Develop Proposal Documentation | On Track | All | 100% | 2024-02-29 | 5
Collect References | On Track | All | 100% | 2024-02-29 | 5
Simulation Development
Create the CAN bus model | On Track | Goran Novakovic | 100% | 2024-03-05 | 7
Model the Transmitter and Receiver | On Track | Clifford Gilbert | 100% | 2024-03-05 | 14
Model the BPSK Signal Processing Conversion | On Track | Andrew Cline | 100% | 2024-03-10 | 7
Create the data encryption model | On Track | Clifford Gilbert | 100% | 2024-03-19 | 7
Create data transfer from integer to data signal | On Track | Clifford Gilbert | 100% | 2024-03-26 | 3
Develop Progress Report Documentation | On Track | All | 100% | 2024-03-25 | 7
Simulation Testing
Test run Transmitter Conversion Model | Low Risk | Andrew Cline | 25% | 2024-03-26 | 10
Test run Receiver Conversion Model | Low Risk | Goran Novakovic | 50% | 2024-03-26 | 10
Update the Simulink Model based on Test Runs | On Track | All | 0% | 2024-03-31 | 5
Run test cases through the completed Simulink Model | On Track | Clifford Gilbert | 0% | 2024-04-05 | 1
Create Project Report Draft | On Track | All | 0% | 2024-04-10 | 6
Project Github Repository
Create Github Repository | On Track | Clifford Gilbert | 100% | 2024-03-22 | 1
Upload Completed Simulink Models | On Track | Goran Novakovic | 0% | 2024-04-06 | 14
Upload PDFs of Milestone Reports (5 Total) | On Track | Andrew Cline | 60% | 2024-03-29 | 31
Upload Supporting Documentation (Gantt Chart, Diagrams, etc.) | On Track | All | 50% | 2024-03-29 | 25
Result Analysis
Review the Results of the Simulink Model | On Track | All | 0% | 2024-04-06 | 2
Calculate the success rate of the Simulink Model | On Track | Goran Novakovic | 0% | 2024-04-08 | 2
Develop Diagrams of Results | On Track | Andrew Cline | 0% | 2024-04-08 | 3
Develop PowerPoint Presentation | On Track | All | 0% | 2024-04-11 | 5
Develop Project Report Documentation | On Track | All | 0% | 2024-04-15 | 15